PPH-26.2

CRM / MES Integration

Master Implementation Plan

Version 3.0  |  March 2026  |  Flexible Packaging Division

| 23 / 32 Steps Built | 11 Bugs → Fix First | 15 New Tables | 9 Weeks Total |
| --- | --- | --- | --- |

# 1. Role-Based View Model

The system enforces two tiers of access across every module. The gate condition is: role ∈ FULL_ACCESS_ROLES AND designation_level ≥ 6. This is already implemented in CRMModule.jsx and must be consistently applied to all new and refactored views.

## 1.1 Access Tier Definitions

| Tier | Roles | Level | What They See | Can Do |
| --- | --- | --- | --- | --- |
| MANAGEMENT (Tier 1) | admin, manager, sales_manager, sales_coordinator | ≥ 6 | All teams, all customers, all inquiries, all tasks, all QC samples, all production jobs across all reps | Send leads to any rep, create & assign tasks, allocate projects, approve quotations, full pipeline dashboard, cross-team reports |
| SALES REP (Tier 2) | sales_rep, sales_executive | < 6 | Own customers only, own inquiries, own tasks, own pipeline | Create inquiries, log activities, submit quotations for approval, capture PO, record dispatch |
| QC MANAGER (Tier 1) | qc_manager + level ≥ 6 | ≥ 6 | All QC samples all divisions, all CSEs, NCR list | Approve/reject CSE, assign QC tasks to analysts, view full QC dashboard with team metrics |
| QC ANALYST (Tier 2) | quality_control, qc_lab | < 6 | Samples assigned to them or in QC inbox, own analyses | Perform analysis, submit results, cannot approve CSE |
| PRODUCTION MGR (Tier 1) | production_manager + level ≥ 6 | ≥ 6 | All job cards, all production jobs, all material checks | Create job cards, approve job cards, advance MES phases, assign operators |
| PROCUREMENT (Tier 2) | stores_keeper, procurement | any | Purchase requisitions and orders related to own department | Raise PR, create PO, confirm material receipt |
| ADMIN (Super) | admin | any | Everything system-wide | All actions including user management and system config |

## 1.2 Role Check — Single Source of Truth

All role checks MUST use these helpers. Never hardcode role strings inline in components or routes.

### Backend: server/routes/mes/presales/_helpers.js  +  server/services/crmAccessControl.js

| Function | Logic | Used In |
| --- | --- | --- |
| isManagement(user) | FULL_ACCESS_ROLES.includes(role) && level >= 6 | All routes — data scoping |
| isAdminOrMgmt(user) | ['admin','manager','sales_manager'].includes(role) | Approval gates |
| canApproveQuotation(user) | isAdminOrMgmt(user) | quotations.js approve/reject |
| canCreateJobCard(user) | ['admin','manager','production_manager','sales_manager'].includes(role) | jobCards.js |
| canApproveMaterial(user) | ['admin','procurement','stores_keeper'].includes(role) | materialOrders.js |
| canAccessQCDashboard(user) | role in QC_ROLES or department ILIKE '%qc%' | _helpers.js |
| canApproveQCStage(user) | ['admin','manager','qc_manager'].includes(role) | cse.js |
| buildRepScopeWhere(user,p) | isManagement → no filter; else → sales_rep_group_id=$p | All list queries |

### Frontend: src/utils/roleChecks.js  +  src/utils/roleConstants.js

| Export | Usage |
| --- | --- |
| isManagement(user) | CRMModule, InquiryBoard, QCDashboard — controls whether rep filter is shown |
| CRM_FULL_ACCESS_ROLES | Tab visibility, lead assignment, task allocation |
| QC_ROLES | QC module access |
| PRODUCTION_ROLES | Job card access |
| MIS_MIN_LEVEL (= 6) | ProtectedRoute minLevel check |

## 1.3 Management View — What They See Per Module

### CRM Module (isManagement = true)

Tabs: Overview (SalesCockpit), All Customers, Prospects (all reps), Deals Pipeline (all reps), Inquiries (all reps + rep filter dropdown), Team, Analytics, Reports, Budget

- Rep filter dropdown: visible only to management. Selecting 'All' shows everything; selecting a rep scopes all lists.

- Lead Assignment: 'Assign to Rep' button on any Prospect or Customer card. Opens a dropdown of active sales reps.

- Task Allocation: 'New Task' modal has Assign To field (rep selector). Reps only see tasks assigned to them.

- Project Allocation: 'Link Inquiry' action on Deal. Management can re-assign inquiry ownership to another rep.

- Full Pipeline Dashboard: funnel chart, cycle times, stalled items, revenue forecast — management only.

- Cross-rep activities feed: ActivityFeed shows events from all reps with rep name badge.

### CRM Module (isManagement = false — Sales Rep)

Tabs: My Day, My Customers, My Prospects, My Pipeline (deals + inquiries merged), My Performance

- All data pre-scoped to own sales_rep_group_id. Rep cannot see another rep's customers.

- No rep filter dropdown. No assign-to-rep controls.

- Tasks: only tasks where assigned_to = req.user.id.

- Inquiries: only inquiries where sales_rep_group_id = own group.

### MES PreSales / QC (isManagement = true)

InquiryBoard: Rep filter dropdown, columns show all inquiries across all reps with rep name on card. Approval queue for quotations and job cards visible in sidebar.

QC Dashboard: all samples all reps, CSE approval queue, SLA breach alerts for all analysts, NCR management across all labs.

### MES PreSales / QC (isManagement = false — Sales Rep)

InquiryBoard: only own inquiries. No rep filter. Cards do not show rep name. Actions limited to: submit for QC, record customer response, capture PO, capture dispatch.

QC Dashboard: QC analysts see only samples in QC inbox that are unassigned or assigned to them. Cannot approve CSE.

### Production Module (isManagement = true — Production Manager level 6+)

Job Card list: all job cards all reps. Filter by status, product group, delivery date. Create Job Card button. Approve Job Card button.

- Material check overview: see all BOM lines across all jobs, highlight not-available.

- MES Flow board: all active production jobs with phase indicators.

- Assign operator to job phase.

### Production Module (isManagement = false — Operator / Procurement)

Operator: only jobs assigned to their phase/machine. Cannot approve job cards.

Procurement: only purchase requisitions and purchase orders. Receipt confirmation.

# 2. Codebase Audit — Status of All 32 Pipeline Steps

| # | Step | File | Status |
| --- | --- | --- | --- |
| 1 | Prospect creation | MyProspects.jsx + crm/prospects.js | ✅ Built |
| 2 | Technical Brief capture | TechnicalBriefForm.jsx + technical-briefs.js | ✅ Built |
| 3 | Deal pipeline creation | DealPipeline.jsx + crm/deals.js | ✅ Built |
| 4 | Inquiry creation (3-step wizard) | InquiryCapture.jsx + inquiries.js | ✅ Built |
| 5 | TDS / attachment upload | SamplesSection.jsx + attachments.js | ✅ Built |
| 6 | SAR print + QR label | SamplesSection.jsx + samples.js | ✅ Built |
| 7 | Batch submit to QC lab | samples.js POST /submit-to-qc | ✅ Built |
| 8 | QC inbox batch receive | QCDashboard.jsx + qc.js | ✅ Built |
| 9 | QR scan → redirect to analysis | QCScanPage.jsx | ⚠️ BUG-02 |
| 10 | Full QC analysis form | QCSampleAnalysis.jsx + qc.js | ✅ Built |
| 11 | CSE auto-generation on analysis submit | qc.js POST /analyses/:id/submit | ✅ Built |
| 12 | QC Manager CSE approval | cse.js POST /cse/:id/approve | ⚠️ BUG-01 |
| 13 | Production Manager final approval | cse.js POST /cse/:id/approve | ✅ Built |
| 14 | Pre-sales clearance | ClearanceSection.jsx + inquiries.js | ✅ Built |
| 15 | MOQ check | checks.js | ✅ Built |
| 16 | Material availability check | checks.js | ✅ Built |
| 17 | Quotation creation (estimation) | QuotationPanel.jsx + quotations.js | ✅ Built |
| 18 | Submit quotation for approval | quotations.js | ⚠️ GAP — no /submit endpoint |
| 19 | Manager approve quotation | quotations.js POST /approve | ⚠️ Incomplete — no reject/revise |
| 20 | Quotation PDF | presalesPdfService.js | ⚠️ GAP — no DRAFT watermark, no quotation type |
| 21 | Send quotation to customer | quotations.js POST /send | ✅ Built |
| 22 | Customer response (accept/reject/counter) | quotations.js POST /customer-response | ✅ Built |
| 23 | Negotiation versioning | quotations.js | ⚠️ GAP — no parent_quotation_id, no version_number |
| 24 | Proforma Invoice creation | ProformaPanel.jsx + proforma.js | ✅ Built |
| 25 | PO confirmation (Proforma) | proforma.js POST /confirm | ✅ Built |
| 26 | Customer PO capture (formal) | — | ❌ MISSING — no mes_customer_purchase_orders |
| 27 | Pre-production sample | PreprodSamplePanel.jsx + preprod.js | ✅ Built |
| 28 | Pre-prod sample approval | preprod.js | ✅ Built |
| 29 | Job Card creation | — | ❌ MISSING — no mes_job_cards table |
| 30 | Material procurement flow | — | ❌ MISSING — no PR/PO/receipt tables |
| 31 | MES production phases (17 phases) | flow.js | ✅ Built (not linked to pre-sales) |
| 32 | Dispatch / Deliver / Close | proforma.js orders routes | ⚠️ Incomplete — no transporter/AWB fields |

# 3. Critical Bugs — Fix Before Any New Feature

ALL bugs in this section must be resolved before Phase 1 work begins. They cause data corruption or broken workflow gates today.

## 3.1 P0 — Data Integrity Bugs (Day 1)

### P0-01 — SQL Placeholder Missing $ Prefix

| Field | Detail |
| --- | --- |
| File | server/routes/crm/index.js (legacy) → now distributed across crm/customers.js, crm/dashboard.js, crm/prospects.js |
| Root Cause | WHERE cu.sales_rep_group_id = ${paramIndex} should be = $${paramIndex}. Without the dollar sign, Postgres receives the literal string '${paramIndex}' and the query fails silently, returning wrong or empty data. |
| Impact | Sales reps see wrong customers. Managers may see all or no data depending on group_id. |
| Fix | Global search: = ${paramIndex} → replace with = $${paramIndex}. Verify with: login as rep whose group_id ≠ 1 and confirm only own customers returned. |
| Effort | 15 minutes |
| Test | Login as rep group_id=3, GET /api/crm/customers — must return only group 3 customers |

### P0-02 — ReferenceError: salesRep.full_name

| Field | Detail |
| --- | --- |
| File | server/routes/crm/index.js line ~1592 (now in crm/customers.js or crm/dashboard.js) |
| Root Cause | salesRep.full_name used but variable is repInfo.fullName. Throws ReferenceError in production silently caught by Express. |
| Fix | Single variable rename: salesRep.full_name → repInfo.fullName |
| Effort | 5 seconds |

### P0-03 — resolveRepGroup() Uses ILIKE Fuzzy Match

| Field | Detail |
| --- | --- |
| File | server/services/crmService.js resolveRepGroup() |
| Root Cause | Fuzzy first-name match → wrong group ID assigned when two reps share first name or name changes in HR system. |
| Fix | (1) Migration crm-007 already added sales_rep_group_id column to crm_sales_reps. (2) Populate all active reps: UPDATE crm_sales_reps SET sales_rep_group_id = (SELECT id FROM sales_rep_groups WHERE ...). (3) Update resolveRepGroup() to use direct ID first, fall back to fuzzy only when column is NULL. Use buildRepScopeWhere() helper everywhere. |
| Effort | 2 hours |

## 3.2 BUG — Pre-Sales Workflow Bugs (Day 2)

### BUG-01 — Production Manager Never Notified of CSE Approval

| Field | Detail |
| --- | --- |
| File | server/routes/mes/presales/cse.js line 189 |
| Root Cause | Status check is 'pending_qc' but should be 'pending_qc_manager'. Production Managers receive zero notifications. |
| Fix | Change one string: 'pending_qc' → 'pending_qc_manager' |
| Effort | 5 minutes |

### BUG-02 — QR Scan Bypasses Full CSE Approval Chain

| Field | Detail |
| --- | --- |
| File | src/components/MES/PreSales/QCScanPage.jsx |
| Root Cause | QR scan page has a 'Submit Testing Result' button that directly marks a sample as tested without creating an analysis record, generating a CSE, or going through management approval. Completely bypasses the QC workflow. |
| Fix | Remove the result submission block from QCScanPage entirely. Replace testing card with Alert component + 'Open Full Analysis Form' button linking to /mes/qc/samples/:id. |
| Effort | 2 hours |

### BUG-03 — Template product_group Filter Ignored

| Field | Detail |
| --- | --- |
| File | server/routes/mes/presales/templates.js |
| Root Cause | Query param product_group passed but not used in SQL WHERE. Wrong template auto-loads for most product groups. |
| Fix | Add: AND ($1 = ANY(product_groups) OR product_groups IS NULL) when query param provided. |
| Effort | 30 minutes |

### BUG-04 — QC Inbox Shows All Divisions

| Field | Detail |
| --- | --- |
| File | server/routes/mes/presales/qc.js GET /qc/inbox |
| Root Cause | No division filter. FP QC lab sees samples from HC and other divisions. |
| Fix | Add: AND i.division = 'FP' to WHERE clause (or parameterise for multi-division support). |
| Effort | 15 minutes |

### BUG-05 — Double Email Notification on Sample Status Patch

| Field | Detail |
| --- | --- |
| File | server/routes/mes/presales/samples.js PATCH /:id/status |
| Root Cause | notifyQCSamplesReceived called both in batch submit-to-qc route AND in individual patch. Customer / QC team receives duplicate emails. |
| Fix | Remove notifyQCSamplesReceived block from individual PATCH route. Keep only in POST /inquiries/:id/submit-to-qc. |
| Effort | 30 minutes |

### ISS-01 — Sales Rep Not Notified When QC Analysis Completed

| Field | Detail |
| --- | --- |
| File | server/routes/mes/presales/qc.js POST /analyses/:id/submit |
| Root Cause | After CSE creation, owner of the inquiry is never notified. Rep has no way to know QC is done without polling the system. |
| Fix | After CSE creation: query inquiry owner → notifyUsers([ownerId], {type:'qc_result_ready', inquiry_id, inquiry_number, customer_name}). |
| Effort | 1 hour |

### ISS-02 — Clearance Restricted to admin Role Only

| Field | Detail |
| --- | --- |
| File | server/routes/mes/presales/inquiries.js PATCH /clearance |
| Root Cause | !isAdminOrMgmt check passes for admin only. sales_manager and manager with level 6+ are blocked. |
| Fix | Replace role check with: isManagement(req.user) (which checks FULL_ACCESS_ROLES AND level >= 6). |
| Effort | 30 minutes |

# 4. Gap Analysis — Missing Features

| ID | Gap | Priority | Source | Phase |
| --- | --- | --- | --- | --- |
| G-01 | Quotation submit/reject/revise endpoints + mes_quotation_approvals audit table | CRITICAL | Req Doc §1 | Phase 1 |
| G-02 | Quotation PDF DRAFT watermark + approver name | HIGH | Req Doc §2 | Phase 1 |
| G-03 | Negotiation versioning: parent_quotation_id, version_number, negotiation_round | HIGH | Req Doc §3 | Phase 1 |
| G-04 | Customer PO capture: mes_customer_purchase_orders table + ±5% validation | CRITICAL | Req Doc §4 | Phase 2 |
| G-05 | Job Card creation: mes_job_cards table + routes + UI | CRITICAL | Both plans | Phase 3 |
| G-06 | Material procurement: mes_purchase_requisitions + mes_supplier_pos + mes_stock_receipts | CRITICAL | Both plans | Phase 4 |
| G-07 | CRM Deal ↔ Inquiry auto-sync (no bidirectional link exists) | CRITICAL | Req Doc §7 | Phase 2 |
| G-08 | Full Pipeline Dashboard (funnel, cycle times, stalled items, revenue forecast) | HIGH | Req Doc §8 | Phase 5 |
| G-09 | Dispatch fields: transporter_name + awb_number on deliver endpoint | HIGH | Req Doc §9 | Phase 2 |
| G-10 | Customer delivery feedback: mes_delivery_feedback table + form | MEDIUM | Req Doc §9 | Phase 2 |
| G-11 | SLA breach scheduled job + OVERDUE badge in QC | HIGH | Original plan | Phase 1 |
| G-12 | CustomerInquiries.jsx: live stage + New Inquiry CTA | MEDIUM | Original plan | Phase 1 |
| G-13 | Lead Assignment: Assign-to-Rep button (management only) | HIGH | New requirement | Phase 2 |
| G-14 | Task Allocation: Assign-to field in task form (management only) | HIGH | New requirement | Phase 2 |
| G-15 | MES production flow linked to Job Card (inquiry_stage auto-updates) | HIGH | Both plans | Phase 5 |

NAMING CONFLICT RESOLVED: The term 'Purchase Order' is used for two different things. The plan uses:

- mes_customer_purchase_orders — the customer's formal PO document confirming the sale (G-04)

- mes_purchase_requisitions — internal request for materials

- mes_supplier_purchase_orders — PO raised to external material suppliers

# 5. Database Migrations

Migrations run in order. Each is idempotent (CREATE TABLE IF NOT EXISTS). Last existing migration number is 319 in the main sequence and crm-013 in the CRM sequence.

## 5.1 Migration: crm-014-rep-scope-fix.js

Ensures sales_rep_group_id is populated for all active reps. Pre-requisite for P0-03 fix.

ALTER TABLE crm_sales_reps ADD COLUMN IF NOT EXISTS sales_rep_group_id INTEGER;

UPDATE crm_sales_reps sr SET sales_rep_group_id = (SELECT id FROM sales_rep_groups WHERE division='FP' AND group_name ILIKE '%'||split_part(sr.full_name,' ',1)||'%' LIMIT 1) WHERE sales_rep_group_id IS NULL;

## 5.2 Migration: mes-presales-012-quotation-workflow.js

Adds quotation approval workflow tables and versioning columns.

- ALTER TABLE mes_quotations ADD COLUMN IF NOT EXISTS parent_quotation_id INTEGER REFERENCES mes_quotations(id)

- ALTER TABLE mes_quotations ADD COLUMN IF NOT EXISTS version_number INTEGER DEFAULT 1

- ALTER TABLE mes_quotations ADD COLUMN IF NOT EXISTS negotiation_round INTEGER DEFAULT 0

- ALTER TABLE mes_quotations ADD COLUMN IF NOT EXISTS submitted_by INTEGER, submitted_at TIMESTAMPTZ

- ALTER TABLE mes_quotations ADD COLUMN IF NOT EXISTS rejected_by INTEGER, rejected_at TIMESTAMPTZ, rejection_reason TEXT

- ALTER TABLE mes_quotations ADD COLUMN IF NOT EXISTS revision_notes TEXT

- CREATE TABLE mes_quotation_approvals (id SERIAL PK, quotation_id INT FK, action VARCHAR(30) CHECK (IN 'submitted','approved','rejected','revision_requested'), actor_id INT, actor_name VARCHAR(255), notes TEXT, created_at TIMESTAMPTZ DEFAULT NOW())

## 5.3 Migration: mes-presales-013-customer-po.js

Customer's formal Purchase Order document.

- CREATE TABLE mes_customer_purchase_orders (id SERIAL PK, po_number VARCHAR(100) NOT NULL, po_date DATE NOT NULL, inquiry_id INT FK mes_presales_inquiries, quotation_id INT FK mes_quotations, po_value NUMERIC(15,2), currency VARCHAR(10) DEFAULT 'USD', delivery_address TEXT, requested_delivery_date DATE, attachment_id INT FK mes_presales_attachments, status VARCHAR(20) DEFAULT 'active', value_deviation_pct NUMERIC(5,2), created_by INT, created_at TIMESTAMPTZ DEFAULT NOW())

## 5.4 Migration: mes-presales-014-dispatch-feedback.js

Extends dispatch and adds delivery feedback.

- ALTER TABLE mes_presales_inquiries ADD COLUMN IF NOT EXISTS transporter_name VARCHAR(255)

- ALTER TABLE mes_presales_inquiries ADD COLUMN IF NOT EXISTS awb_number VARCHAR(100)

- ALTER TABLE mes_presales_inquiries ADD COLUMN IF NOT EXISTS dispatch_date DATE

- ALTER TABLE mes_presales_inquiries ADD COLUMN IF NOT EXISTS expected_delivery_date DATE

- CREATE TABLE mes_delivery_feedback (id SERIAL PK, inquiry_id INT FK, satisfaction_rating SMALLINT CHECK(1..5), feedback_text TEXT, reorder_likelihood VARCHAR(10) CHECK(IN 'yes','maybe','no'), captured_by INT, captured_at TIMESTAMPTZ DEFAULT NOW())

## 5.5 Migration: crm-015-deal-sync.js

Adds note column to crm_deal_stage_history for system-generated entries.

- ALTER TABLE crm_deal_stage_history ADD COLUMN IF NOT EXISTS note TEXT

- ALTER TABLE crm_deal_stage_history ADD COLUMN IF NOT EXISTS source VARCHAR(20) DEFAULT 'manual' CHECK(IN 'manual','system')

## 5.6 Migration: mes-presales-015-job-cards.js

Job Card table — production work orders.

- CREATE TABLE mes_job_cards (id SERIAL PK, job_card_number VARCHAR(30) UNIQUE NOT NULL, inquiry_id INT FK, quotation_id INT FK, customer_po_id INT FK mes_customer_purchase_orders, cse_id INT FK mes_cse_reports, product_name VARCHAR(255), product_group VARCHAR(100), run_quantity NUMERIC(15,3), quantity_unit VARCHAR(20) DEFAULT 'Kgs', delivery_date DATE, material_bom JSONB DEFAULT '[]', print_colors INT, substrate VARCHAR(255), dimensions VARCHAR(100), special_instructions TEXT, status VARCHAR(30) DEFAULT 'draft' CHECK(IN 'draft','pending_approval','approved','in_production','completed','cancelled'), mes_job_id INT REFERENCES mes_jobs(id), approved_by INT, approved_at TIMESTAMPTZ, created_by INT, created_at TIMESTAMPTZ DEFAULT NOW(), updated_at TIMESTAMPTZ DEFAULT NOW())

material_bom JSONB structure: [{material_name, spec, required_qty, unit, available_qty, status: 'available'|'not_available'|'ordered'|'received', pr_id, po_id}]

## 5.7 Migration: mes-presales-016-procurement.js

Material procurement chain.

- CREATE TABLE mes_purchase_requisitions (id SERIAL PK, pr_number VARCHAR(30) UNIQUE, job_card_id INT FK mes_job_cards, items JSONB DEFAULT '[]', total_estimated_value NUMERIC(15,2), status VARCHAR(20) DEFAULT 'draft' CHECK(IN 'draft','pending_approval','approved','partially_ordered','fully_ordered'), requested_by INT, approved_by INT, approved_at TIMESTAMPTZ, created_at TIMESTAMPTZ DEFAULT NOW())

- CREATE TABLE mes_supplier_purchase_orders (id SERIAL PK, po_number VARCHAR(30) UNIQUE, pr_id INT FK, supplier_name VARCHAR(255), items JSONB DEFAULT '[]', total_amount NUMERIC(15,2), currency VARCHAR(10) DEFAULT 'USD', expected_delivery_date DATE, actual_delivery_date DATE, status VARCHAR(20) DEFAULT 'draft' CHECK(IN 'draft','pending_approval','approved','sent','acknowledged','received','cancelled'), created_by INT, approved_by INT, created_at TIMESTAMPTZ DEFAULT NOW())

- CREATE TABLE mes_stock_receipts (id SERIAL PK, supplier_po_id INT FK, received_by INT, received_date DATE, items JSONB DEFAULT '[]', notes TEXT, created_at TIMESTAMPTZ DEFAULT NOW())

## 5.8 Migration: mes-presales-017-sla-tracking.js

Tracks sent_to_qc_at for SLA calculation.

- ALTER TABLE mes_presales_samples ADD COLUMN IF NOT EXISTS sent_to_qc_at TIMESTAMPTZ

- CREATE INDEX IF NOT EXISTS idx_mes_qc_analyses_sla ON mes_qc_analyses(sla_due_at) WHERE sla_due_at IS NOT NULL

# 6. Phased Implementation Plan

| Phase | Name | Duration | Goal | Block? |
| --- | --- | --- | --- | --- |
| Phase 0 | Critical Bug Fixes | Day 1–2 | Fix all 7 bugs. No new features until done. | Yes — blocks everything |
| Phase 1 | Quotation Workflow + QC Notifications | Week 1 | Submit/reject/revise quotation, PDF watermark, SLA breach job, CustomerInquiries upgrade | No |
| Phase 2 | Deal Sync + Customer PO + Dispatch | Week 2 | Bidirectional deal-inquiry sync, customer PO capture, dispatch fields, delivery feedback | No |
| Phase 3 | Job Card + Estimation UI + Quotation PDF | Week 3–4 | Job Card full CRUD, PDF generation, negotiation versioning, estimation dedicated view | No |
| Phase 4 | Material Procurement Flow | Week 5 | PR → manager approve → supplier PO → receipt → job confirmed | No |
| Phase 5 | Pipeline Dashboard + MES Link + Enhancements | Week 6–7 | Full pipeline funnel, MES flow linked to job card, lead assignment, task allocation | No |
| Phase 6 | Refactoring + Test Coverage | Week 8–9 | Route splitting, dead code removal, unit + integration + E2E test suite | No |

## Phase 0 — Critical Bug Fixes (Day 1–2)

Rule: each fix is a separate PR. No mixing fixes. PRs are merged in order P0-01 → P0-02 → P0-03 → BUG-01 → BUG-02 → BUG-03 → BUG-04 → BUG-05 → ISS-01 → ISS-02.

| Task | File(s) to Edit | Accept Criterion |
| --- | --- | --- |
| P0-01: Fix $ prefix in parameterised SQL | server/routes/crm/customers.js, prospects.js, dashboard.js, activities.js | login as rep group_id=3 → see only group 3 customers |
| P0-02: Fix salesRep.full_name ReferenceError | server/routes/crm/customers.js or dashboard.js | No ReferenceError in server logs for any crm endpoint |
| P0-03: resolveRepGroup() direct ID lookup | server/services/crmService.js + crm-014-rep-scope-fix migration | Reps with identical first names get correct group |
| BUG-01: Fix CSE notification status string | server/routes/mes/presales/cse.js | Production Manager receives SSE notification after QC manager approves CSE |
| BUG-02: Remove result submission from QCScanPage | src/components/MES/PreSales/QCScanPage.jsx | QR scan page shows only 'Open Analysis Form' link, no submit button |
| BUG-03: Fix template product_group filter | server/routes/mes/presales/templates.js | Correct template loads for BOPP, PET, PA/PE separately |
| BUG-04: Add division filter to QC inbox | server/routes/mes/presales/qc.js | FP QC inbox shows only FP samples |
| BUG-05: Remove double notification | server/routes/mes/presales/samples.js | Single email on batch submit, none on individual patch |
| ISS-01: Notify sales rep on QC complete | server/routes/mes/presales/qc.js | Sales rep receives SSE after analysis submitted |
| ISS-02: Fix clearance role check | server/routes/mes/presales/inquiries.js | sales_manager with level 6 can grant clearance |

## Phase 1 — Quotation Workflow + QC Notifications (Week 1)

### P1-1: Quotation Submit / Reject / Revise Endpoints

- POST /quotations/:id/submit — Sales Rep submits draft → pending_approval. Validates: status must be 'draft'. Notifies all isAdminOrMgmt users. Inserts into mes_quotation_approvals.

- POST /quotations/:id/reject — Manager only. Status → 'rejected'. Stores rejection_reason. Notifies submitter. Logs in mes_quotation_approvals.

- POST /quotations/:id/request-revision — Manager only. Status → 'draft'. Stores revision_notes. Notifies submitter.

- PATCH /quotations/:id/send — Guard: status must be 'approved'. Remove current loophole that sends draft quotations.

- GET /quotations/:id/approval-history — Returns all mes_quotation_approvals entries for a quotation.

File: server/routes/mes/presales/quotations.js (add 4 new endpoints)

### P1-2: Quotation PDF — DRAFT Watermark + Approver Name

- In server/services/presalesPdfService.js: detect quotation.status !== 'approved' → render diagonal DRAFT — NOT FOR CUSTOMER watermark (red 45° rotated text).

- When status = 'approved': render approved by: [approver_name] on [approved_at] in footer.

- Add company header with logo to quotation PDF (re-use CSE PDF header pattern).

File: server/services/presalesPdfService.js

### P1-3: Quotation Versioning for Negotiation

- POST /quotations/:id/create-revision — Creates a new mes_quotations record with parent_quotation_id = :id, version_number = parent.version_number + 1, negotiation_round = parent.negotiation_round + 1, status = 'draft'. Copies all fields from parent.

- QuotationPanel.jsx: show version history list. Show original price vs revised price. Show negotiation_round badge.

- NegotiationTimeline.jsx (new component): vertical timeline showing all quotation versions, customer counter-offers, manager decisions. Rendered on InquiryDetail.

Files: quotations.js (1 new endpoint), QuotationPanel.jsx (edit), NegotiationTimeline.jsx (new)

### P1-4: SLA Breach Scheduled Job

- New file: server/jobs/slaBreachChecker.js — runs every 30 minutes via setInterval in index.js.

- Query: SELECT * FROM mes_qc_analyses WHERE sla_due_at < NOW() AND overall_result IS NULL.

- For each overdue analysis: notifyRoleUsers(['qc_manager','manager'], {type:'sla_breach', ...}).

- QCDashboard.jsx: add red OVERDUE badge when NOW() > sla_due_at and analysis not submitted.

Files: server/jobs/slaBreachChecker.js (new), src/components/MES/QC/QCDashboard.jsx (edit)

### P1-5: CustomerInquiries.jsx — Full Integration

- Show live inquiry_stage badge with colour coding per stage group.

- Show PhaseStepperCard: horizontal stepper showing which of 6 macro-phases (QC / Clearance / Quotation / PO / Production / Delivered) is active.

- Show 'Action Needed' flag when inquiry is waiting for current user's action.

- 'New Inquiry' button opens InquiryCapture with customer pre-filled.

- Management view: shows inquiries across all reps for this customer. Rep filter not needed here (scoped to customer).

File: src/components/CRM/CustomerInquiries.jsx (edit)

### P1-6: Management — Lead Assignment

- Add 'Assign to Rep' button on ProspectManagement.jsx and CustomerList.jsx (management only — isManagement check).

- Opens modal: dropdown of active crm_sales_reps. On confirm: PATCH /crm/prospects/:id or /crm/customers/:id with { assigned_rep_id }.

- Backend: crm/prospects.js + crm/customers.js — update assigned rep, log in crm_activities with type 'lead_assigned'.

- SSE notification to newly assigned rep: 'You have been assigned a new lead: [Customer Name]'.

Files: ProspectManagement.jsx (edit), crm/prospects.js (edit), crm/customers.js (edit)

## Phase 2 — Deal Sync + Customer PO + Dispatch (Week 2)

### P2-1: CRM Deal ↔ Inquiry Auto-Sync

Create server/services/dealSyncService.js with the following exported function:

- syncDealFromInquiry(inquiryId, newStage, client) — looks up crm_deals WHERE inquiry_id = :inquiryId AND stage NOT IN ('won','lost'). Maps inquiry stage to deal stage:

  - estimation / quoted / negotiating → deal.stage = 'negotiation'

  - order_confirmed / in_production / ready_dispatch / delivered → deal.stage = 'won', closes deal with reason 'PO confirmed via [inquiry_number]'

  - lost → deal.stage = 'lost'

- Inserts into crm_deal_stage_history with source='system'.

- Called from: pipeline.js (stage advance), proforma.js (confirm), quotations.js (customer-response accepted).

- InquiryBoard badge: pass linked deal stage to DealCard.jsx via joined query — show inquiry_stage badge on DealCard.

- DealDetail unified timeline: GET /api/crm/deals/:id/unified-timeline merges crm_activities + mes_presales_activity_log for linked inquiry, sorted by timestamp DESC.

- 'Link to Existing Inquiry' on DealCreateModal — dropdown of unlinked inquiries for same customer.

Files: server/services/dealSyncService.js (new), pipeline.js (edit), proforma.js (edit), quotations.js (edit), DealCard.jsx (edit), crm/deals.js (new endpoint)

### P2-2: Customer PO Capture

- New file: server/routes/mes/presales/customerPO.js

- POST /customer-po — requires: po_number, po_date, inquiry_id, quotation_id. Optional: po_value, delivery_address, requested_delivery_date, attachment.

- Validation: fetch accepted quotation total. If abs(po_value - total) / total > 0.05 → return warning (not error). Client shows yellow warning banner.

- On success: advance inquiry_stage to order_confirmed. Log activity. Call dealSyncService.syncDealFromInquiry.

- Notify: Sales Manager, Production Manager, stores_keeper role.

- If attachment provided: store as inquiry attachment with type 'purchase_order'.

- CustomerPOPanel.jsx (new): shown on InquiryDetail when stage = price_accepted or sample_approved. Form with fields. After submission shows PO summary card.

Files: server/routes/mes/presales/customerPO.js (new), src/components/MES/PreSales/InquiryDetail/CustomerPOPanel.jsx (new), mes/presales/index.js (mount new router)

### P2-3: Dispatch Fields + Customer Notification

- Extend POST /orders/:inquiryId/deliver in proforma.js: add transporter_name, awb_number, dispatch_date to request body. Store on mes_presales_inquiries.

- After stage → 'delivered': if inquiry has linked customer contact with email → send dispatch notification email (emailService.js) with tracking details.

- Sales rep SSE notification with tracking number.

File: server/routes/mes/presales/proforma.js (edit deliver endpoint)

### P2-4: Delivery Feedback

- POST /orders/:inquiryId/feedback — accepts: satisfaction_rating (1-5), feedback_text, reorder_likelihood. Stores in mes_delivery_feedback.

- DeliveryFeedbackPanel.jsx (new): shown on InquiryDetail when stage = 'delivered'. Star rating widget + textarea + three-option button group.

- Full Pipeline Dashboard (Phase 5) uses aggregate feedback scores per rep for management view.

Files: proforma.js (new endpoint), src/components/MES/PreSales/InquiryDetail/DeliveryFeedbackPanel.jsx (new)

### P2-5: Task Allocation (Management → Reps)

- Extend crm/tasks.js POST /tasks: add assigned_to field. Management can set this to any user ID.

- GET /tasks?mine=true: for non-management, filter WHERE assigned_to = req.user.id OR created_by = req.user.id.

- GET /tasks (management): returns all tasks with assigned_to user name populated via JOIN.

- TaskCreateModal.jsx: add 'Assign To' rep selector dropdown when isManagement. Default: current user.

- TaskWidget.jsx: show 'Assigned by [name]' badge on tasks assigned by management.

- SSE notification to assigned user.

Files: crm/tasks.js (edit), TaskCreateModal.jsx (edit), TaskWidget.jsx (edit)

## Phase 3 — Job Card + Estimation UI + Quotation PDF (Week 3–4)

### P3-1: Job Card Backend

- New file: server/routes/mes/presales/jobCards.js

- POST /job-cards — role check: canCreateJobCard(user). Auto-generates job_card_number: JC-FP-{YEAR}-{NNNNN}. Auto-populates: product_name, substrate, dimensions from inquiry + CSE. material_bom from mes_presales_material_checks. run_quantity from accepted quotation. delivery_date from customer PO.

- GET /job-cards — Management: all. Rep: only job cards for own inquiries.

- GET /job-cards/:id — full detail with material_bom expanded.

- PATCH /job-cards/:id — update only when status = 'draft'. Validates no read-only fields changed.

- POST /job-cards/:id/approve — role: canCreateJobCard(user) AND isManagement. Status → 'approved'. Creates mes_jobs entry. Sets inquiry_stage → 'in_production'. Calls dealSyncService. Notifies all production depts + sales rep.

- PATCH /job-cards/:id/material-status — Updates individual BOM line status. If all lines available → auto-approve materials and notify production manager.

File: server/routes/mes/presales/jobCards.js (new, ~280 lines)

### P3-2: Job Card UI

- JobCardPanel.jsx — tab on InquiryDetail (visible after order_confirmed). Shows: status badge, material BOM table with availability indicators (green/red/orange dots), delivery date, 'Create Job Card' button (management only).

- JobCardForm.jsx — Create / edit form. Pre-fills from inquiry + quotation + CSE. Editable BOM table (management can add/remove lines). 'Submit for Approval' button.

- JobCardPDF.jsx — A4 printable using jsPDF. Header with logo, job number, customer, delivery date. Specifications table. Material BOM table. Print parameters. Two signature blocks (Production Manager / QC). Download as PDF button.

- JobCardList.jsx — Management view at /mes/job-cards. Table with columns: JC Number, Inquiry, Customer, Status, Delivery Date, Material Status. Filters: status, date range. Click row → JobCardForm.

Files: InquiryDetail/JobCardPanel.jsx (new), JobCardForm.jsx (new), JobCardPDF.jsx (new), JobCardList.jsx (new), MES/index.jsx (add route)

### P3-3: Estimation UI — Dedicated Estimator View

- New route /mes/estimation — protected, accessible to admin + sales_manager + sales_coordinator.

- EstimationQueue.jsx — lists all inquiries at 'estimation' or 'cse_approved' stage. Management sees all reps; rep sees own.

- EstimationForm.jsx — cost calculation table: material cost (kg * price), conversion cost (m²), overhead percentage, target margin percentage. Live unit price calculation. 'Create Quotation' button saves estimation data as JSONB snapshot on mes_quotations.estimation_data column.

- ALTER TABLE mes_quotations ADD COLUMN IF NOT EXISTS estimation_data JSONB — stores full cost breakdown for PDF generation.

Files: EstimationQueue.jsx (new), EstimationForm.jsx (new), MES/index.jsx (add route)

## Phase 4 — Material Procurement Flow (Week 5)

### P4-1: Procurement Backend

- New file: server/routes/mes/presales/procurement.js

- POST /purchase-requisitions — auto-created when Job Card BOM has not_available lines. Also manually creatable by procurement role. pr_number: PR-FP-{YEAR}-{NNNNN}. Notifies procurement manager + manager.

- POST /purchase-requisitions/:id/approve — manager role. Status → 'approved'. Notifies procurement team.

- POST /supplier-purchase-orders — procurement role. Linked to approved PR. po_number: SPO-FP-{YEAR}-{NNNNN}.

- POST /supplier-purchase-orders/:id/approve — manager role. Notifies procurement to send to supplier.

- POST /supplier-purchase-orders/:id/send — status → 'sent'. Optionally emails supplier.

- POST /stock-receipts — stores_keeper role. Records received quantities. Updates job card BOM lines. If all BOM lines received: job card material_status → 'available'. Notifies production manager.

- GET /purchase-requisitions?job_card_id=N — management sees all, procurement sees own

- GET /supplier-purchase-orders?pr_id=N — role-scoped

File: server/routes/mes/presales/procurement.js (new, ~350 lines)

### P4-2: Procurement UI

- ProcurementPanel.jsx — Tab on InquiryDetail (visible after job card created). Shows PR status, PO status, expected delivery date. 'Raise PR' button (procurement role only). Management sees full procurement chain.

- PurchaseRequisitionForm.jsx — Create / edit PR. Auto-populates from job card BOM not_available lines. Editable.

- SupplierPurchaseOrderForm.jsx — Create PO from approved PR. Select supplier, set unit prices, expected delivery date.

- StockReceiptForm.jsx — Storekeeper form. Lists PO lines. Input received quantities. Submit.

- ProcurementDashboard.jsx — Management only at /mes/procurement. Open PRs, POs awaiting approval, pending deliveries, overdue receipts.

Files: InquiryDetail/ProcurementPanel.jsx (new), PurchaseRequisitionForm.jsx (new), SupplierPurchaseOrderForm.jsx (new), StockReceiptForm.jsx (new), ProcurementDashboard.jsx (new), MES/index.jsx (add route)

## Phase 5 — Pipeline Dashboard + MES Link + Enhancements (Week 6–7)

### P5-1: Full Pipeline Dashboard (Management Only)

- New route /crm/pipeline-dashboard — protected: isManagement AND level >= 6.

- Backend: GET /api/crm/pipeline-dashboard — returns:

  - funnel_counts: { opportunity, technical_assessment, estimation_quotation, order_processing, production, delivery } — counts from crm_deals and mes_presales_inquiries

  - avg_cycle_times: average days per phase computed from stage_changed_at timestamps

  - stalled_items: inquiries where stage_changed_at < NOW() - 7 days, sorted by days_in_stage DESC

  - revenue_forecast: SUM(accepted quotation values) WHERE inquiry_stage IN ('order_confirmed','in_production','ready_dispatch')

  - phase_drill: on click of funnel phase → GET /api/crm/pipeline-dashboard?phase=production → returns individual inquiry list

- FullPipelineDashboard.jsx: Recharts FunnelChart for phase counts. CycleTimeBar chart. StalledItemsTable with deep link to inquiry. RevenueForecastCard. Management only tab in CRMModule.

Files: crm/dashboard.js (new endpoint), FullPipelineDashboard.jsx (new), CRMModule.jsx (add tab)

### P5-2: MES Flow Engine Linked to Job Card

- In POST /job-cards/:id/approve: after inserting into mes_jobs, set mes_jobs.job_card_id = job_card_id, mes_jobs.inquiry_id = inquiry_id.

- Extend mes/flow.js advance-phase handler: on each phase advance, call UPDATE mes_presales_inquiries SET inquiry_stage = 'in_production', updated_at = NOW() (for phases < dispatch) or 'ready_dispatch' (for final production phase).

- SSE notification to sales rep on each phase advance: 'Production update: [job_number] advanced to [phase_name]'.

Files: server/routes/mes/presales/jobCards.js (edit approve handler), server/routes/mes/flow.js (edit advance handler)

### P5-3: QC Enhancements

- ENH-01: FP-specific parameter presets — in QCTemplateAdmin, add preset templates for BOPP, PET, PA/PE, CPP with parameters: thickness (μm), tensile MD/TD (N/mm²), elongation MD/TD (%), COF static/kinetic, ΔE colour, ink adhesion (%), seal strength (N/15mm), OTR (cc/m²/day), MVTR (g/m²/day).

- ENH-02: Solvent retention auto-warning — in qc.js POST /analyses/:id/submit: if solvent_retention_value > 10 (mg/m²) AND product is food-contact → append warning to CSE notes and flag cse.has_safety_warning = TRUE.

- ENH-03: CSE PDF — add company logo + signature block (QC Manager + Production Manager) using presalesPdfService.

- ENH-04: Sample disposition — ALTER TABLE mes_presales_samples ADD COLUMN disposition VARCHAR(20) CHECK(IN 'retain','return','dispose'). QCSampleAnalysis.jsx: add disposition selector before submitting.

Files: QCTemplateAdmin.jsx (edit), qc.js (edit submit), presalesPdfService.js (edit CSE PDF), QCSampleAnalysis.jsx (edit)

## Phase 6 — Refactoring + Test Coverage (Week 8–9)

### P6-1: Code Health — Route File Size Enforcement

No route file should exceed 300 lines. Current violations and their remediation:

| File | Current Lines | Split Into |
| --- | --- | --- |
| server/routes/mes/presales/qc.js | ~420 | qc-inbox.js (receive/scan), qc-analysis.js (CRUD + submit), qc-cse.js (split from cse.js) |
| server/routes/mes/presales/proforma.js | ~480 | proforma.js (PI create/send/confirm), orders.js (ready-dispatch, deliver, feedback, close) |
| server/routes/mes/presales/quotations.js | ~450 | quotations.js (CRUD + PDF), quotation-approval.js (submit/approve/reject/revision) |
| server/routes/mes/presales/inquiries.js | ~520 | inquiries-core.js (CRUD + stage), inquiries-clearance.js (clearance + MOQ + material), inquiries-admin.js (stats + management views) |

### P6-2: Shared Helpers Consolidation

- buildRepScopeWhere(user, paramIndex) in server/services/crmAccessControl.js — returns {clause, params}. Replace every inline rep-scoping WHERE clause across all route files.

- generateSequenceNumber(prefix, sequenceName, client) in server/utils/sequenceGenerator.js — replace duplicated numbering logic in quotations.js, jobCards.js, procurement.js.

- standardNotify(inquiryId, eventType, extraData, client) in server/services/mesNotificationService.js — wraps notifyUsers + notifyRoleUsers + logActivity in one call.

### P6-3: Frontend Dead Code Removal

- Remove AdminCRMDashboard.jsx and CRMDashboard.jsx inline duplication — both now delegate to SalesCockpit.jsx with props { isAdmin, lockedGroupId }. Saves ~40KB.

- Remove dead recentActivities state in MyDayDashboard.jsx.

- Remove dead getCustomerSearchNames() function in crm/customers.js.

- Remove unused http/https imports in crm/ routes (legacy from original monolith).

- Consolidate inline role checks: replace all component-level ['admin','manager'].includes(user?.role) with imported roleChecks.js functions.

### P6-4: CSS Architecture Cleanup

- All CRM component styles in src/components/CRM/CRM.css using naming: .crm-{component}-{element}.

- All MES PreSales styles in src/components/MES/PreSales/PresalesInquiries.css.

- No inline styles except dynamic values (colors from data, calculated widths).

- New components from Phases 1–5 must follow these conventions.

# 7. Testing Plan

Every phase ships with corresponding tests. No phase is 'done' until tests pass.

## 7.1 Unit Tests — server/tests/unit/

| Test File | Covers | Key Cases |
| --- | --- | --- |
| crm/crmAccessControl.test.js | buildRepScopeWhere(), isManagement() | rep vs manager scoping, level boundary (5 vs 6) |
| crm/resolveRepGroup.test.js | P0-03 direct ID lookup | direct match, fuzzy fallback, null handling |
| mes/quotationApproval.test.js | submit/approve/reject/revise state machine | invalid transitions, duplicate submissions |
| mes/dealSync.test.js | syncDealFromInquiry() | each stage mapping, already-won deal skip, missing FK |
| mes/customerPO.test.js | ±5% validation | exact match, 4.9%, 5.1%, no PO value provided |
| mes/jobCard.test.js | BOM auto-population, number generation | empty BOM, partial availability, sequence collision |
| mes/procurement.test.js | PR→PO→receipt chain | full receipt, partial receipt, receipt triggers job confirm |
| mes/slaBreachChecker.test.js | overdue detection | overdue, due in future, already-submitted skipped |

## 7.2 Integration Tests — server/tests/integration/

| Test File | Workflow Tested |
| --- | --- |
| quotationWorkflow.test.js | Draft → submit → approve → send → customer response → create-revision → approve revision → send revised |
| customerPOFlow.test.js | price_accepted → capture PO → order_confirmed → deal syncs to 'won' |
| jobCardFlow.test.js | order_confirmed → create job card → approve → mes_job created → in_production stage |
| procurementFlow.test.js | job card BOM not_available → auto-PR created → approve PR → create SPO → receive → BOM available → notify prod mgr |
| dealInquirySync.test.js | Create deal → link inquiry → advance inquiry stages → verify deal stage at each point |
| rbacRoutes.test.js | Each restricted endpoint returns 403 for wrong role, 200 for correct role |

## 7.3 End-to-End Tests — server/tests/e2e/

| Test | Persona | Steps |
| --- | --- | --- |
| Full Sales Cycle | Sales Rep + Sales Manager | Prospect → Inquiry → QC → Clearance → Quotation (approve cycle) → Customer PO → Job Card → Dispatch → Close |
| Management Pipeline View | Sales Manager (level 7) | Login → open Full Pipeline Dashboard → verify funnel counts → click production phase → verify stalled items → assign task to rep |
| QC Workflow | QC Analyst + QC Manager | Sample batch receive → full analysis → CSE generated → QC Manager approves → Production Manager approves → Rep notified |
| Procurement Chain | Production Manager + Procurement + Storekeeper | Job card approved with not-available BOM → PR auto-created → Manager approves → SPO created → Storekeeper receives → Job confirmed |
| Role Isolation | Sales Rep A | Login as Rep A → attempt to view Rep B's customer → must get 403. Attempt to approve quotation → must get 403. |

## 7.4 Phase Verification Checklists

### After Phase 0 — run before any Phase 1 work begins

- Login as sales rep with group_id ≠ 1 → confirm only own customers visible

- Submit samples as rep → QC Manager approves CSE → Production Manager receives SSE notification (BUG-01 fixed)

- QR scan sample URL → confirm NO submit result button, only 'Open Analysis Form' link (BUG-02 fixed)

- Server logs show no ReferenceError: salesRep.full_name

- FP QC inbox shows only FP division samples

- Individual sample PATCH generates one email, not two

- sales_manager with designation_level=6 can grant clearance

### After Phase 1

- Sales rep submits quotation → manager receives in-app notification with quotation details

- Manager rejects quotation with reason → rep receives notification + rejection_reason visible

- Manager requests revision → quotation back to draft, revision_notes visible in mes_quotation_approvals history

- Draft quotation PDF shows diagonal DRAFT watermark

- Approved quotation PDF shows approver name

- QC analyst submits analysis → sales rep receives SSE 'qc_result_ready'

- QC sample with sla_due_at in past shows red OVERDUE badge in QCDashboard

- Management assigns lead via 'Assign to Rep' → assigned rep receives SSE notification

### After Phase 2

- Inquiry advances to 'quoted' → linked crm_deal.stage updates to 'negotiation'

- Inquiry advances to 'order_confirmed' → linked deal.stage = 'won', close reason = 'PO confirmed via [number]'

- Capture PO with value 12% higher than quotation total → yellow warning banner shown (not blocked)

- Capture PO with correct value → inquiry_stage → order_confirmed

- Mark dispatch with transporter + AWB → customer contact receives tracking email

- Management task assigned to rep → rep sees it in TaskWidget with 'Assigned by [name]' badge

### After Phase 3

- Production Manager creates job card from order_confirmed inquiry → BOM pre-populated

- Job card approved → mes_jobs entry created, inquiry_stage = in_production, all production depts notified

- Print job card PDF → A4 renders correctly with specs, BOM, signature blocks

- Estimator opens /mes/estimation → enters costs → creates quotation with estimation_data snapshot

### After Phase 4

- Job card BOM has not_available line → PR auto-created → Procurement Manager notified

- Manager approves PR → Procurement team notified

- Supplier PO created → Manager approves → marked sent

- Storekeeper records full receipt → all BOM lines → available → Job confirmed → Production Manager notified → Sales Rep notified

### After Phase 5

- Full Pipeline Dashboard shows correct funnel counts from live data

- Stalled items list shows inquiries stuck > 7 days with correct days_in_stage

- Revenue forecast matches SUM of accepted quotations at order_confirmed+ stages

- Production phase advance (flow.js) updates inquiry_stage and notifies sales rep

### After Phase 6 — Regression

- All Phase 0 verification checklist items still pass

- All API endpoints still return expected data after route splitting

- No inline role checks remain in components (all use roleChecks.js functions)

- No CSS file has rules for components outside its designated scope

- npm test returns 0 failures

# 8. Complete Notification Map

| Event | Trigger | Channel | Recipients | Status |
| --- | --- | --- | --- | --- |
| Samples submitted to QC | POST /inquiries/:id/submit-to-qc | Email + SSE | QC Lab, QC Mgr, Manager | ✅ Built |
| QC analysis complete → CSE | POST /qc/analyses/:id/submit | SSE | QC roles | ✅ Built |
| QC analysis complete → Rep | POST /qc/analyses/:id/submit | SSE | Sales Rep (owner) | ⚠️ ISS-01 → Phase 0 |
| QC Mgr approved → Prod Mgr | POST /cse/:id/approve | SSE | Production Mgr, Manager | ⚠️ BUG-01 → Phase 0 |
| Prod Mgr final approval → Rep | POST /cse/:id/approve | SSE | Sales Rep | ✅ Built |
| Clearance granted | PATCH /inquiries/:id/clearance | SSE | Sales Rep | ✅ Built |
| SLA breach | Job every 30 min | SSE | QC Mgr, Manager | ❌ Phase 1 |
| Quotation submitted for approval | POST /quotations/:id/submit | SSE + Email | All Sales Managers | ❌ Phase 1 |
| Quotation approved | POST /quotations/:id/approve | SSE | Sales Rep | ✅ Built |
| Quotation rejected | POST /quotations/:id/reject | SSE | Sales Rep (submitter) | ❌ Phase 1 |
| Lead assigned to rep | PATCH /prospects/:id or /customers/:id | SSE | Assigned Sales Rep | ❌ Phase 1 |
| Task assigned to rep | POST /tasks | SSE | Assigned user | ❌ Phase 2 |
| PO confirmed (Proforma) | POST /proforma-invoices/:id/confirm | SSE | Production Mgr, Manager | ✅ Built |
| Customer PO captured | POST /customer-po | SSE + Email | Sales Mgr, Production Mgr, Procurement | ❌ Phase 2 |
| Dispatch with tracking | POST /orders/:id/deliver | Email | Customer contact, Sales Rep | ❌ Phase 2 |
| Job Card created | POST /job-cards | SSE | Production Mgr, Manager, Storekeeper | ❌ Phase 3 |
| Job Card approved | POST /job-cards/:id/approve | SSE | All production depts, Sales Rep | ❌ Phase 3 |
| Material not in stock → PR | BOM check on job card | SSE | Procurement Mgr, Manager | ❌ Phase 4 |
| PR approved | POST /purchase-requisitions/:id/approve | SSE | Procurement team | ❌ Phase 4 |
| SPO approved | POST /supplier-pos/:id/approve | SSE + Email | Procurement, Supplier | ❌ Phase 4 |
| Materials fully received | POST /stock-receipts | SSE | Production Mgr, Manager, Sales Rep | ❌ Phase 4 |
| Production phase advance | POST /mes/jobs/:id/advance | SSE | Sales Rep | ❌ Phase 5 |
| Pre-prod sample sent | PATCH /preprod-samples/:id/status | SSE | Sales Rep | ✅ Built |
| Pre-prod sample approved | POST /preprod-samples/:id/customer-response | SSE | Production, Manager | ✅ Built |

# 9. Complete File Inventory

## 9.1 Files to EDIT (Bug Fixes + Enhancements)

| File | Phase | Change Summary |
| --- | --- | --- |
| server/routes/crm/customers.js | P0 | Fix $${paramIndex}, fix salesRep.full_name, add 'Assign to Rep' endpoint |
| server/routes/crm/prospects.js | P0, P1 | Fix $${paramIndex}, add 'Assign to Rep' endpoint |
| server/routes/crm/dashboard.js | P0 | Fix $${paramIndex}, add /pipeline-dashboard endpoint (Phase 5) |
| server/routes/crm/deals.js | P2 | Add /unified-timeline endpoint, 'link-inquiry' action |
| server/routes/crm/tasks.js | P2 | Add assigned_to field, scope tasks by assignment for reps |
| server/services/crmService.js | P0 | Fix resolveRepGroup() to use direct ID |
| server/services/crmAccessControl.js | P0, P6 | Add buildRepScopeWhere(), isManagement() exported |
| server/routes/mes/presales/_helpers.js | P0 | Add isManagement(), canCreateJobCard(), canApproveMaterial() |
| server/routes/mes/presales/cse.js | P0 | Fix BUG-01: 'pending_qc' → 'pending_qc_manager' |
| server/routes/mes/presales/qc.js | P0, P1 | Fix BUG-04 division filter, add ISS-01 rep notification, SLA breach endpoint |
| server/routes/mes/presales/samples.js | P0 | Fix BUG-05 double notification |
| server/routes/mes/presales/inquiries.js | P0 | Fix ISS-02 clearance role check |
| server/routes/mes/presales/templates.js | P0 | Fix BUG-03 product_group filter |
| server/routes/mes/presales/quotations.js | P1, P3 | Add submit/reject/revise/create-revision endpoints, enforce approved-only send |
| server/routes/mes/presales/pipeline.js | P2 | Call dealSyncService on stage advance |
| server/routes/mes/presales/proforma.js | P2 | Add transporter_name, awb_number, customer notification to deliver; add feedback endpoint |
| server/routes/mes/presales/index.js | P2–P4 | Mount customerPO.js, jobCards.js, procurement.js routers |
| server/routes/mes/flow.js | P5 | Call dealSyncService + update inquiry_stage on phase advance |
| server/services/presalesPdfService.js | P1, P3 | Add DRAFT watermark, approver name, quotation PDF type, CSE logo + signature |
| server/jobs/crmDailyDigest.js | P1 | Add SLA breach check call |
| src/utils/roleChecks.js | P0, P1 | Add isManagement(), canCreateJobCard() exports |
| src/utils/roleConstants.js | P0 | Add PROCUREMENT_ROLES, ensure MIS_MIN_LEVEL = 6 |
| src/components/CRM/CRMModule.jsx | P1, P5 | Add Full Pipeline Dashboard tab (management only) |
| src/components/CRM/ProspectManagement.jsx | P1 | Add 'Assign to Rep' button (management only) |
| src/components/CRM/CustomerList.jsx | P1 | Add 'Assign to Rep' button (management only) |
| src/components/CRM/CustomerInquiries.jsx | P1 | Full integration: live stage, phase stepper, New Inquiry CTA |
| src/components/CRM/TaskCreateModal.jsx | P2 | Add 'Assign To' rep selector (management only) |
| src/components/CRM/TaskWidget.jsx | P2 | Show 'Assigned by [name]' badge |
| src/components/CRM/DealCard.jsx | P2 | Show inquiry_stage badge when deal has linked inquiry |
| src/components/MES/PreSales/QCScanPage.jsx | P0 | Remove result submission, replace with 'Open Analysis Form' link |
| src/components/MES/PreSales/InquiryBoard.jsx | P2 | Add inquiry_stage badge to deal cards, rep filter (management only) |
| src/components/MES/PreSales/InquiryDetail/index.jsx | P1–P4 | Add tabs: CustomerPOPanel, JobCardPanel, ProcurementPanel, DeliveryFeedbackPanel |
| src/components/MES/QC/QCDashboard.jsx | P1 | Add OVERDUE badge, management vs analyst view scoping |
| src/components/MES/QC/QCSampleAnalysis.jsx | P5 | Add disposition selector (ENH-04) |
| src/components/MES/QC/QCTemplateAdmin.jsx | P5 | Add FP-specific parameter presets (ENH-01) |
| src/components/MES/index.jsx | P3–P4 | Add routes for JobCardList, EstimationQueue, ProcurementDashboard |

## 9.2 Files to CREATE (New Components and Services)

| File | Phase | Purpose |
| --- | --- | --- |
| server/migrations/crm-014-rep-scope-fix.js | P0 | Populate sales_rep_group_id for all active reps |
| server/migrations/mes-presales-012-quotation-workflow.js | P1 | parent_quotation_id, version_number, mes_quotation_approvals table |
| server/migrations/mes-presales-013-customer-po.js | P2 | mes_customer_purchase_orders table |
| server/migrations/mes-presales-014-dispatch-feedback.js | P2 | transporter/awb columns, mes_delivery_feedback table |
| server/migrations/crm-015-deal-sync.js | P2 | note + source columns on crm_deal_stage_history |
| server/migrations/mes-presales-015-job-cards.js | P3 | mes_job_cards table |
| server/migrations/mes-presales-016-procurement.js | P4 | mes_purchase_requisitions, mes_supplier_purchase_orders, mes_stock_receipts tables |
| server/migrations/mes-presales-017-sla-tracking.js | P1 | sent_to_qc_at column, SLA index |
| server/routes/mes/presales/quotation-approval.js | P1 | submit / reject / revise / approval-history endpoints |
| server/routes/mes/presales/customerPO.js | P2 | Customer PO capture CRUD |
| server/routes/mes/presales/jobCards.js | P3 | Job Card CRUD + approve + material-status |
| server/routes/mes/presales/procurement.js | P4 | PR / SPO / receipt endpoints |
| server/services/dealSyncService.js | P2 | syncDealFromInquiry() function |
| server/services/mesNotificationService.js | P6 | standardNotify() wrapper function |
| server/utils/sequenceGenerator.js | P6 | generateSequenceNumber() shared utility |
| server/jobs/slaBreachChecker.js | P1 | 30-min interval SLA breach detector |
| server/tests/unit/crmAccessControl.test.js | P6 | Unit tests for buildRepScopeWhere, isManagement |
| server/tests/unit/quotationApproval.test.js | P6 | Unit tests for quotation state machine |
| server/tests/unit/dealSync.test.js | P6 | Unit tests for syncDealFromInquiry |
| server/tests/unit/customerPO.test.js | P6 | Unit tests for ±5% validation |
| server/tests/unit/jobCard.test.js | P6 | Unit tests for BOM population and number generation |
| server/tests/unit/procurement.test.js | P6 | Unit tests for PR→PO→receipt chain |
| server/tests/integration/quotationWorkflow.test.js | P6 | Integration: full quotation approval cycle |
| server/tests/integration/customerPOFlow.test.js | P6 | Integration: PO capture → deal sync |
| server/tests/integration/jobCardFlow.test.js | P6 | Integration: job card create → approve → MES job |
| server/tests/integration/procurementFlow.test.js | P6 | Integration: full procurement chain |
| server/tests/integration/dealInquirySync.test.js | P6 | Integration: bidirectional deal sync |
| server/tests/integration/rbacRoutes.test.js | P6 | Integration: 403 for wrong roles on all restricted endpoints |
| server/tests/e2e/fullSalesCycle.test.js | P6 | E2E: Prospect → Closed across all personas |
| src/components/MES/PreSales/NegotiationTimeline.jsx | P1 | Vertical timeline of quotation versions |
| src/components/MES/PreSales/InquiryDetail/CustomerPOPanel.jsx | P2 | Customer PO capture form + status |
| src/components/MES/PreSales/InquiryDetail/DeliveryFeedbackPanel.jsx | P2 | Delivery feedback star rating form |
| src/components/MES/PreSales/JobCardForm.jsx | P3 | Job card create/edit form with BOM table |
| src/components/MES/PreSales/JobCardPanel.jsx | P3 | Job card status tab on InquiryDetail |
| src/components/MES/PreSales/JobCardPDF.jsx | P3 | jsPDF printable job card A4 |
| src/components/MES/PreSales/JobCardList.jsx | P3 | Management view of all job cards |
| src/components/MES/PreSales/EstimationQueue.jsx | P3 | Queue of inquiries awaiting estimation |
| src/components/MES/PreSales/EstimationForm.jsx | P3 | Cost calculation table with live unit price |
| src/components/MES/PreSales/InquiryDetail/ProcurementPanel.jsx | P4 | PR/PO status tab on InquiryDetail |
| src/components/MES/PreSales/PurchaseRequisitionForm.jsx | P4 | Create/edit PR |
| src/components/MES/PreSales/SupplierPurchaseOrderForm.jsx | P4 | Create PO from approved PR |
| src/components/MES/PreSales/StockReceiptForm.jsx | P4 | Storekeeper receipt confirmation |
| src/components/MES/PreSales/ProcurementDashboard.jsx | P4 | Management procurement overview |
| src/components/CRM/FullPipelineDashboard.jsx | P5 | Funnel, cycle times, stalled items, revenue forecast |

# 10. Coding Rules — Every File, Every Commit

| Rule | Detail |
| --- | --- |
| Small files | Every route file ≤ 300 lines. Split when approaching limit. No God files. |
| Small PRs | Each PR = one atomic change. Never mix a bug fix with a new feature in the same PR. |
| Parameterised queries | ALWAYS use $1, $2 placeholders. NEVER interpolate ${} into SQL strings. NEVER concatenate SQL. |
| Transactions | All writes touching >1 table: BEGIN / COMMIT / ROLLBACK. On any error: ROLLBACK before returning 500. |
| Role checks | ALWAYS import from roleChecks.js (frontend) or _helpers.js (backend). Never hardcode role strings inline. |
| Scoped queries | ALWAYS use buildRepScopeWhere() helper for any query that lists customers, inquiries, tasks, or deals. Never write the WHERE rep filter inline. |
| Notifications | Every status change affecting another person MUST fire a notification. No silent stage transitions. |
| SSE labels | Every new notification type must be added to MESNotificationBell.jsx typeLabel map before the PR is merged. |
| CSS naming | CRM: .crm-{component}-{element} in CRM.css. MES: .presales-{component}-{element} in PresalesInquiries.css. No inline styles except dynamic values. |
| Soft delete | Never DELETE or destructive UPDATE without: soft-delete (is_deleted flag) or explicit user-initiated confirmation with a confirm dialog. |
| Audit trail | All presales state changes: call logActivity(). All CRM mutations: call logAudit(). All deal stage changes: insert crm_deal_stage_history. |
| Error responses | All errors return { success: false, error: '<message>' }. All 403s log the attempt. All 500s log the full stack trace. |
| Test before ship | Before marking any task done: (1) happy path, (2) missing required field → 400, (3) unauthorised role → 403, (4) run npm test. |
| No data loss | No migration runs DELETE or DROP without explicit is_deleted soft-delete migration first. Keep all data. |
| Migration numbering | CRM migrations: crm-014, crm-015... MES migrations: mes-presales-012, mes-presales-013... Never reuse a number. |

# 11. Sprint Schedule

| Week | Phase | Tasks | Output |
| --- | --- | --- | --- |
| Week 1 — Days 1–2 | Phase 0 | P0-01 → ISS-02 (all 10 bug fixes, one PR each) | All critical bugs resolved, zero wrong-data risk |
| Week 1 — Days 3–5 | Phase 1 (Part 1) | P1-1: quotation submit/reject/revise, P1-2: PDF watermark, P1-3: versioning | Quotation workflow enforced end-to-end |
| Week 1 — Days 4–5 | Phase 1 (Part 2) | P1-4: SLA breach job, P1-5: CustomerInquiries, P1-6: Lead assignment | Notifications live, management can assign leads |
| Week 2 | Phase 2 | P2-1: Deal sync, P2-2: Customer PO, P2-3: Dispatch fields, P2-4: Delivery feedback, P2-5: Task allocation | Bidirectional sync live, PO captured, dispatch tracked |
| Weeks 3–4 | Phase 3 | P3-1+2: Job Card backend + UI, P3-3: Estimation view, run Phase 3 verification | Job Card working, estimation dedicated view |
| Week 5 | Phase 4 | P4-1: Procurement backend, P4-2: Procurement UI, run Phase 4 verification | Full material procurement chain live |
| Weeks 6–7 | Phase 5 | P5-1: Pipeline Dashboard, P5-2: MES flow link, P5-3: QC enhancements | Full pipeline visible to management, loop complete |
| Weeks 8–9 | Phase 6 | P6-1–P6-4: Refactoring, test suite, verification regression run | Clean codebase, test coverage ≥ 80%, all checklists pass |

Total: 9 weeks from Phase 0 kickoff to Phase 6 completion.

Parallel tracks: After Phase 0, Phases 1 and 2 can overlap if two developers are available. Phase 3 depends on Phase 2 (needs Customer PO table). Phase 4 depends on Phase 3 (needs Job Card table). Phase 5 depends on Phase 4.

# Appendix — End-to-End Workflow Reference

Complete 32-step pipeline from Prospect to Closed order.

| # | Stage | Actor | System | Notification Sent To |
| --- | --- | --- | --- | --- |
| 1 | Prospect created (exhibition / referral / cold call) | Sales Rep | CRM: fp_prospects | — |
| 2 | Technical Brief captured (substrate, dimensions, volume) | Sales Rep | CRM: crm_technical_briefs | — |
| 3 | Deal created & linked to prospect | Sales Rep | CRM: crm_deals | — |
| 4 | Prospect approved by manager → convert to Customer | Sales Manager | CRM: fp_customer_unified | Sales Rep |
| 5 | Inquiry created (3-step wizard) | Sales Rep | MES: mes_presales_inquiries | — |
| 6 | TDS / samples uploaded | Sales Rep | MES: mes_presales_samples | — |
| 7 | SAR printed with QR label | Sales Rep | MES: SAR PDF | — |
| 8 | Batch samples submitted to QC | Sales Rep | MES: samples status → sent_to_qc | QC Lab, QC Mgr, Manager |
| 9 | QC inbox: batch receive samples | QC Analyst | MES: status → qc_received | — |
| 10 | QR scan → Open full analysis form | QC Analyst | MES: redirect to QCSampleAnalysis | — |
| 11 | Full QC analysis completed | QC Analyst | MES: mes_qc_analyses | Sales Rep (ISS-01) |
| 12 | CSE auto-generated | System | MES: mes_cse_reports | — |
| 13 | QC Manager reviews + approves CSE | QC Manager | MES: cse status → qc_manager_approved | Production Manager, Manager |
| 14 | Production Manager final approval | Prod Manager | MES: cse status → approved | Sales Rep |
| 15 | Pre-sales clearance granted | Sales Manager (level 6+) | MES: presales_cleared = true | Sales Rep |
| 16 | MOQ check completed | Management | MES: mes_presales_moq_checks | — |
| 17 | Material availability check | Management | MES: mes_presales_material_checks | — |
| 18 | Estimation: unit price calculated | Estimator / Sales Mgr | MES: mes_quotations.estimation_data | — |
| 19 | Quotation created (draft) | Sales Rep / Estimator | MES: mes_quotations status → draft | — |
| 20 | Sales Rep submits quotation for approval | Sales Rep | MES: status → pending_approval | All Sales Managers (NEW) |
| 21 | Manager approves quotation | Sales Manager | MES: status → approved | Sales Rep |
| 22 | Quotation sent to customer | Sales Rep | MES: status → sent | — |
| 23 | Customer response: accepted / rejected / counter | Sales Rep records | MES: status → accepted/rejected/counter_offer | — |
| 24 | If counter: escalate to manager, create revision | Sales Rep | MES: new quotation with parent_quotation_id (NEW) | Sales Manager |
| 25 | Manager approves revised quotation | Sales Manager | MES: revised quotation → approved | Sales Rep |
| 26 | Customer accepts final quotation | Sales Rep | MES: inquiry → price_accepted | — |
| 27 | Proforma Invoice created and sent | Sales Rep | MES: mes_proforma_invoices | Customer (email) |
| 28 | Customer PO captured | Sales Rep | MES: mes_customer_purchase_orders (NEW) | Sales Mgr, Prod Mgr, Procurement |
| 29 | Pre-production sample requested + sent | Sales Rep / Production | MES: mes_preprod_samples | Sales Rep |
| 30 | Customer approves pre-prod sample | Sales Rep records | MES: preprod status → approved | Production, Manager |
| 31 | Job Card created from confirmed inquiry | Prod Manager | MES: mes_job_cards (NEW) | All production, Sales Rep |
| 32 | Job Card approved | Prod Manager (level 6+) | MES: mes_jobs created, inquiry → in_production | All production, Sales Rep |
| 33 | If material not in stock → PR auto-created | System | MES: mes_purchase_requisitions (NEW) | Procurement, Manager |
| 34 | PR approved → Supplier PO created → sent | Manager, Procurement | MES: mes_supplier_purchase_orders (NEW) | Procurement, Supplier |
| 35 | Materials received | Storekeeper | MES: mes_stock_receipts (NEW), BOM updated | Prod Manager, Sales Rep |
| 36 | Production phases 1–17 (prepress → dispatch) | Production Operators | MES: mes_jobs phases | Sales Rep (each advance) |
| 37 | Dispatch with transporter + AWB | Production / Logistics | MES: inquiry → delivered | Sales Rep, Customer contact |
| 38 | Customer feedback captured | Sales Rep | MES: mes_delivery_feedback (NEW) | — |
| 39 | Inquiry closed → Deal marked Won | Sales Rep | MES: inquiry → closed; CRM: deal → won | — |

This document is the single source of truth for the PPH-26.2 CRM/MES implementation. All PRs reference phase and task numbers from this document.

Last updated: March 2026 | Owner: Development Lead | Review cycle: end of each phase